## Slide 1
IST 2107 | Case Study
Student Project Management System
Makerere University | College of Computing & Information Sciences
UGX 450M
Budget
10 Months
Duration
9 Modules
Features
5 Presenters
Team
1/13

## Slide 2
Agenda
01
Project Overview
Understanding the SPMS initiative
02
Stakeholder Analysis
Key interests and engagement strategies
03
Project Charter
Objectives, scope, and constraints
04
Work Breakdown Structure
Three-level decomposition
05
Project Schedule
Gantt chart and milestones
06
Risk Management
Risk register and mitigation
07
Communication Plan
Stakeholder engagement framework
08
Methodology
Hybrid approach justification
09
Success Factors
Critical success criteria
10
Reflection
Delay response and lessons learned
2/13

## Slide 3
SECTION A
Project Overview
The Problem
> Students miss important deadlines
> Supervisors exceed recommended workload
> Progress reports are difficult to monitor
> Communication is inconsistent
> Final submissions are delayed
> Records are difficult to retrieve
Why a Project?
> Temporary (10 months, fixed end)
> Unique deliverable (custom system)
> Progressive elaboration
> Resource constraints (budget/time)
> Risk and uncertainty present
The Proposed Solution: SPMS
Online proposal submission
Supervisor allocation
Milestone tracking
Progress reporting
Meeting scheduling
Notifications & reminders
Document management
Project assessment
3/13

## Slide 4
SECTION B
Stakeholder Analysis
Stakeholder
Interest
Power
Influence
University Management
ROI on UGX 450M; improved graduation rates; institutional reputation
High
High
Deputy Principal
Sponsor visibility; on-time delivery; project success
High
High
Students
Easy submission; clear deadlines; timely feedback; transparency
High
Medium
Academic Staff
Manageable workload; efficient communication; fair allocation
Medium
High
ICT Support Unit
Maintainability; integration feasibility; security compliance
Medium
Medium
Department Heads
Smooth operations; workload balance; reporting access
Medium
Medium
4/13

## Slide 5
SECTION A
Project Charter
UGX 450M
Budget
10
Months
9
Features
6
Deliverables
Project Objectives
> Deliver functional SPMS within 10 months
> Complete within UGX 450M budget
> Achieve >=80% user adoption in 3 months post-launch
> Seamless ACMIS integration
> Full data security & privacy compliance
System Features
> Online proposal submission
> Supervisor allocation engine
> Milestone tracking & progress reporting
> Meeting scheduling & notifications
> Document management (version control)
> Project assessment & grading
> Report generation for coordinators
5/13

## Slide 6
SECTION D
Work Breakdown Structure
1
Project Initiation & Planning
1.1 Charter | 1.2 Stakeholder Analysis | 1.3 Requirements | 1.4 Sign-off | 1.5 Plan Baseline
2
System Design
2.1 Database | 2.2 Architecture | 2.3 UI/UX | 2.4 ACMIS Design | 2.5 Design Review
3
Development
3.1 Auth/RBAC | 3.2 Proposals | 3.3 Allocation | 3.4 Milestones | 3.5 Scheduling
3.6 Documents | 3.7 Assessment | 3.8 Reports | 3.9 ACMIS Integration
6/13

## Slide 7
SECTION D (cont.)
Work Breakdown Structure
4
Testing & QA
4.1 Unit | 4.2 Integration | 4.3 System | 4.4 Security | 4.5 Performance | 4.6 UAT
5
Deployment & Training
5.1 Prod Setup | 5.2 Migration | 5.3 Go-Live | 5.4 Training | 5.5 Hypercare
6
Project Closure
6.1 Documentation | 6.2 Lessons Learned | 6.3 ICT Transition | 6.4 Sign-off
Total: 6 major phases | 30+ work packages | 3 levels of decomposition
7/13

## Slide 8
Project Schedule
M1
M2
M3
M4
M5
M6
M7
M8
M9
M10
Initiation & Planning
2 mo
System Design
2 mo
Development
4 mo
Testing & QA
3 mo
Deployment & Training
2 mo
Project Closure
1 mo
Initiation
Design
Development
Testing
Deployment
Closure
8/13

## Slide 9
Project Milestones
MONTH 2
Requirements Baseline Signed
All stakeholder groups sign off on SRS document
MONTH 4
Design Complete & Approved
Architecture, DB, UI, integration designs reviewed & approved
MONTH 6
Core Functionality Demo (Alpha)
All 9 features demonstrable; unit tests >= 80% coverage
MONTH 9
UAT Pass & Go-Live Readiness
UAT sign-off from all 3 user groups; production env ready
MONTH 10
System Live & Project Closure
SPMS in production; zero critical bugs; closure report approved
9/13

## Slide 10
SECTION F
Risk Register
#
Risk Description
Prob.
Impact
Mitigation Strategy
1
Lecturers unavailable during semester
High
High
Schedule workshops during breaks; assign proxy reps
2
ACMIS integration API changes/delays
Medium
High
Early MoU with ICT; adapter layer; mock API
3
Scope creep from stakeholders
High
Medium
Strict CCB; MoSCoW prioritization; scope freeze
4
Resistance to change from senior staff
High
Medium
Early engagement; champions; mandatory training
5
Budget overrun from complexity
Medium
High
Monthly tracking; 10% contingency; Phase 2 deferral
10/13

## Slide 11
Communication Plan
Audience
Frequency
Channel
Owner
Purpose
Sponsor / Deputy Principal
Bi-weekly
Face-to-face + email
PM
Progress & escalations
Development Team
Daily
Stand-up + Slack/Teams
PM
Blockers & sprint progress
Department Heads
Monthly
Email + dept meetings
PM
Status & resource requests
Academic Staff
Monthly
Email + portal
Coordinator
Demos & training schedule
Students
Bi-weekly
Portal + social media
Coordinator
Updates & training dates
ICT Support Unit
Weekly
Slack + sync meetings
Dev Lead
Integration & security
Escalation Path
Level 1: Dev Lead > Project Manager | Level 2: PM > Sponsor | Level 3: Sponsor > University Council
11/13

## Slide 12
SECTION E
Recommended Methodology: Hybrid
Initiation > Design
WATERFALL
Fixed scope & budget
Compliance requirements
Signed baselines needed
Development > Testing
AGILE (SCRUM)
2-week sprints
User feedback loops
Early demos reduce risk
Deployment > Closure
WATERFALL
Irreversible go-live
Fixed training schedule
Formal sign-off required
Why NOT Pure Waterfall?
> Lecturers unavailable during semester
> Users resist change without early demos
> Requirements evolve after first review
Why NOT Pure Agile?
> Fixed budget/deadline needs upfront planning
> ACMIS integration contract is fixed
> University procurement requires specs
12/13

## Slide 13
SECTION H
Critical Success Factors
Executive Sponsorship
Deputy Principal unblocks resources, resolves conflicts, signals importance to resistant staff
Early User Involvement
Lecturers available intermittently; students validate UX; prevents 'built but unused'
Scope & Change Control
Fixed budget/deadline means scope creep = failure; MoSCoW + CCB essential
ACMIS Integration
Single source of truth for student data; failure = duplicate entry, errors, distrust
Training & Change Mgmt
Resistance is a named constraint; champions + workshops drive adoption
Skilled Core Team
Communication kills velocity; dedicated devs + PM + QA = accountability
> = 80%
User Adoption Target
< = 10
Months Duration
100%
Budget Compliance
13/13

## Slide 14
REFLECTION
4-Month Delay: Response Plan
Actions as Project Manager
1. Emergency steering committee meeting
2. Present impact assessment & recovery options
3. Re-baseline: crash or reduce scope to MVP
4. Negotiate new deadline (Month 14)
5. Formal root cause analysis
Affected Knowledge Areas
> Schedule Management - baseline broken
> Scope Management - reduction required
> Stakeholder Mgmt - trust damaged
> Communications - urgent updates needed
> Risk Mgmt - late requirements materialized
Stakeholder Communication
> Sponsor: Face-to-face + formal memo (Day 1)
> Dept Heads: Email + meetings (Day 2)
> Students: Portal announcement (Day 3)
> Dev Team: Stand-up + revised plan (Day 1)
Lessons for Future Projects
> Lock requirements before semester
> MoUs with dependency owners
> Contingency for academic calendar
> Proxy user representatives
> Pilot with 1 department first
14/14

## Slide 15
SECTION G
Triple Constraint
Scope > Cost
Adding 'mobile app' (+UGX 80M) exceeds budget. Requires additional funding or descoping.
Scope > Time
Adding 'plagiarism checker' pushes timeline 6 weeks. Misses academic year deadline.
Scope > Quality
Fixed time/budget + more scope = rushed testing. Data breach risk. Poor UX = low adoption.
Trade-off Triangle
Fixed Time (10 months) + Fixed Cost (UGX 450M) => Scope must be controlled via Change Control Board
Questions & Discussion
Thank you for your attention
15/15